## Slide 1: N-17720 – New 132/33kv KIZAD Substation and Related 132kv Cable Works
20th May 2025

## Slide 2: N-17720 – New 132/33kv KIZAD Substation and Related 132kv Cable Works
TAQA Transmission Scope
New 132/33 kV KIZAD Substation at Khalifa Industrial Zone Abu Dhabi. 132kV Cable works from ODSE to 132kV GIS at Taweelah and Kizad end. LDC Intergration works.
Major Project Highlights
33KV GIS, Telecom Panel, Capacitor Bank, Power Transformer, 132kV GIS, Battery, Auxiliary Transformer, LV Cable, DC Charger, EOT Crane, Fire Pump, Fire Water Tank delivered. Capacitor bank pedestal concrete works completed. Staircase-3 Roof Slab, Parapet & Pedestals upstands Rebar Fixing works completed. 132kV GIS room floor preparation work for painting in progress. Battery room tile work in progress. MEP/LSP work at Cable basement in progress. Auxiliary building & Boundary Wall foundation work in progress. Sandwich Panel erection for ground floor room in progress. Power Transformer Site Testing in progress.
Major Concerns
Main Building Civil Works – 'Sandwich Panel supply mainly for main building internal partition walls are delayed and intern electrical access is delayed. ELMEC to expedite delivery of sandwich panels and provide electrical access which is delayed by 1.5 month.
BACKGROUND | 
Contractor | ELMEC
Consultant | TRACTEBEL
LOA Date | 24.04.2023
Awarded value: | AED 220,500,000.00
Contractual Completion Date | 23.04.2025
Expected Completion Date | 14.10.2025
Project Schedule and Status Update
Overall Completion
Breakdown
Chart: 
| Engineering | Procurement | Construction
Actual | 0.93 | 0.87 | 0.3
Baseline | 1 | 1 | 1
Actual
Planned
Chart: 
Actual | 0.65
Baseline | 1

## Slide 3: N-17720 – New 132/33kV KIZAD Substation and Related 132kv Cable Works
Procurement Status
ACTIVITY | 132kV GIS & LLC |  | 33kV GIS |  | Power Transformer |  | 132kV SCMS System |  | 110V DC System |  | Protection Equipment | 
 | PLAN | Expected/ Actual | PLAN | Expected/ Actual | PLAN | Expected/ Actual | PLAN | Expected/ Actual | PLAN | Expected/ Actual | PLAN | Expected/ Actual
Manufacturing Start | 17.11.2023 | 15.09.2023 | 22.01.2024 | 31.01.2024 | 20.01.2024 | 15.12.2023 | 24.01.2024 | 24.05.2024 | 19.02.2024 | 24.05.2024 | 05.02.2024 | 15.04.2024
FAT | 04.07.2024 | 14.10.2024 | 06.06.2024 | 13.08.2024 | 27.07.2024 | 25.06.2024 | 30.07.2024 | 07.04.2025 | 05.07.2024 | 20.01.2025 | 31.07.2024 | 14.04.2025
Delivery | 17.09.2024 | 08.04.2025 | 24.08.2024 | 15.11.2024 | 14.10.2024 | 20.11.2024 | 14.10.2024 | 07.06.2025 | 18.09.2024 | 11.03.2025 | 13.09.2024 | 30.04.2025
Installation (completion) | 08.11.2024 | 24.06.2025 | 14.11.2024 | 30.06.2025 | 04.12.2024 | 15.04.2025 | 11.12.2024 | 26.06.2025 | 17.10.2024 | 02.06.2025 | 28.10.2024 | 27.05.2025
T&C (Completion) | 07.02.2025 | 15.09.2025 | 15.01.2025 | 15.09.2025 | 09.01.2025 | 03.07.2025 | 14.04.2025 | 30.09.2025 | 31.10.2024 | 16.06.2025 | 07.02.2025 | 27.08.2025
On time
Ahead of schedule
Delayed